## 11_02_22
Danone Market Mix
Sl No | Tasks | Priority | Status
1
2
3
4
5
6
Daily Breakdown of Tasks
Date | Task | Owner | Status | Notes
Monday Feb 7 | Client Empathy
Install Python
External research on problem statement
Tuesday Feb 8
Client Empathy
Tuesday Feb 9
Tuesday Feb 10
Tuesday Feb 11
Tuesday Feb 12
Tuesday Feb 13
Tuesday Feb 14
Tuesday Feb 15
Tuesday Feb 16
Tuesday Feb 17
Tuesday Feb 18
Tuesday Feb 19
Tuesday Feb 20
Tuesday Feb 21
Tuesday Feb 22
Tuesday Feb 23
Tuesday Feb 24
Tuesday Feb 25
Tuesday Feb 26
Tuesday Feb 27
Tuesday Feb 28

## Task_Tracker
Danone Market Mix
Sl No | Tasks | Priority | Status
1
2
3
4
5
6
Daily Breakdown of Tasks
Date | Task | Owner | Status | Notes
2022-02-01 | Capstone Details
Data understanding
| External research on problem statement | Team |  | https://themathcompany.sharepoint.com/:f:/r/knowledge_management/Shared%20Documents/05.%20Delivery%20Artefacts/01.%20Approved%20Artefacts/01.%20Pre-Engagement?csf=1&web=1&e=bHo1mB
| Create project folder and upload all relevant material | Vijetha Arya | Completed
| List of coding/version control best practices | Team | Completed
2022-03-01 | Data dictionary |  |  | https://themathcompany.sharepoint.com/:f:/r/knowledge_management/Shared%20Documents/05.%20Delivery%20Artefacts/01.%20Approved%20Artefacts/03.%20Design?csf=1&web=1&e=NSI3ez
| Consolidate insightful visualizations |  |  | https://themathcompany.sharepoint.com/:f:/r/knowledge_management/Shared%20Documents/05.%20Delivery%20Artefacts/01.%20Approved%20Artefacts/04.%20EDA?csf=1&web=1&e=aUpqan
First readout
Hypothesis testing
Thursday Feb 3 | Understanding of the Problem Statement
Tuesday Feb8 | Client Empathy | TEAM | WIP
Install Python
Friday Feb 11 | Client Empathy | TEAM | COMPLETED | https://themathcompany.sharepoint.com/:p:/s/Capstone_DanoneFrance/ET9NTMvGu_hCvy2YGBssKlMBQeuMzFRDNai7LCZM_3zWXg?e=myP8Qy
2022-03-07 | Volume-Price graph | Viswa | Completed
| price trend graphs for all years | Viswa | Completed
| seperate boxplot for all columns | Viswa | Completed
| functionalize the code | Viswa | Completed
| correlation map | Viswa | Completed
| have a connect with malyasia team | Team | Completed
2022-03-08 | question in Eda task allocation excel | Team
| Connect with Danone,France team | Team
| Organize notebook based on tactic | Chandan | Completed
| Add insites for graphs required | Team
| Promotional Spends for all years | Chandan | Completed
| Consolidate all digital spends | Chandan | Completed
| Update timeline in task tracker | Viswa | Completed
Monday, April 25, 2022 | Connect with Co.dx mentors to: - Finalize model notebook - Get data dict for config file (add as a tab to config file template) | Shyamala | Completed | EOD
| Codify model results generation | Viswa
| Generate first round of model results (decent, explainable) | Team |  | Wed
| Recording model results - build process | Vijetha Arya | Completed | EOD
Thursday,April 28,2022 | Research and code on the best methods for shortlisting the variable for linear regression | Akarsh
| Codify model results generation | Team | Completed
| Generate first round of model results (decent, explainable) | Viswa | Completed
| Print the model results and perfomance metrics | Vijetha Arya | Completed | Fri
| Automate model results and perfomance metrics | Vijetha Arya and Shyamala | Completed | Thu
Friday April 29 | Understanding the summary sheet | viswa & Chandan
| Creating checklist that needs to checked after every iterration | viswa & Chandan
Thursday May 5 | Explaining the ROI code flow | Viswa
| Redo EDA on weekly level and identify the features which plays importance. | Shyamala & Darshan
| Automate model results and perfomance metrics(Contribution alone) & graph | Chandan
Friday,May 6 | Add a random forest model to get the best features | Akarsh
| Automate chi2 selection and understand chi2 | Akarsh
| Automate selection of features through correlation | Akarsh
| Provide recommendations from EDA and try plotting the graphs in excel and automate it to take lag and adstock values | Shyamala
Understanding the summary sheet
Creating checklist that needs to checked after every iterration
Explaining the ROI code flow
Wwdnesday,May 11 | finding the reason for negative Incremental sales | viswa
| Colour coding of variable presnt in the iteration done | Chandan
| Dropdown of DV and IV and input lag and adstock and make coressponding transformation on the selected variables and get the plots and correlation | shyamala | Completed
| Do a random test train split instead of going with time series | Viswa

## Project_Plan
Task | Sub-task | 2022-02-04 | 2022-02-11 | 2022-02-18 | 2022-02-25 | 2022-03-04 | 2022-03-11 | 2022-03-18 | 2022-03-25 | 2022-04-01 | 2022-04-08 | 2022-04-15 | 2022-04-22 | 2022-04-29 | 2022-05-06 | 2022-05-13 | 2022-05-20 | 2022-05-27
Problem Statement Understanding | Capstone Details | bar: 2022-02-04 to 2022-02-25
Data understanding | bar: 2022-02-04 to 2022-02-25
External research on problem statement | bar: 2022-02-04 to 2022-02-25
Data Understanding | Review 1 readout - first draft | bar: 2022-02-04 to 2022-02-25
| Review 1 readout - finalize | 2022-02-25: Review 1: Industry Understanding, Client Understanding & Problem Definition
| Data dictionary | 2022-03-04: WIP
| Consolidate insightful visualizations | 2022-03-04: WIP
Hypothesis testing
Model Building | Feature engineering: - Lag - Adstock | 2022-05-13: Review 3: Model Build (Solution Accuracy, Storyboarding)
| Review 2 readout | 2022-04-08: Review 2: Exploratory Analysis (Solution Approach, Insight Quality, Creativity) + Engineering components as applicable
First model iteration: - Performance metrics - Response curve - Contribution (waterfall chart) | bar: 2022-03-11